## 
ED-3
Sr. No. | District |  | DPR Agency Nominated Person/PMC Agency/PMC Site Engineer/SWSM representative/Contractor Nominated Person |  | INR in crore |  |  | Date of Agreement | Intake/WTP ds fuekZ.k gsrq NOC izkIr gksus dh Date | IIT ls Vet gksdj 55 ,y0ih0lh0Mh0 dh Mh0ih0vkj0 izkIr gksus dk fnukadA |  | Physical Progress | [5 empty] | Land Details | [6 empty] | Financial Progress Status
[5 empty] | DPR Cost | EFC Cost | Tended Bid Cost
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
1 | Mahoba | Shivhar G.O.V. W/S Scheme | DPR Agency Nominated Person | BLG (Mr. Khet Singh. Mob 9956221055) | 340.65 | 241.72 | 242.17 | 2020-06-18 | 2020-08-21 | In process | In process | Activities | Start Date | Unit | Planned | Achieved | % Completed | Detail of work | Item | Unit | Scope | Achieved | balance | % Progress | Mobilisation Amout paid 21.16 cr on 13/07/2020
|  | Chandrawal Dam | PMC Agency | SMEC India | [7 empty] | Rising main Survey | 2020-07-15 | Km | 158.812+increasing | 158.81 | 100 | LAND IDENTIFICATION | INTAKE | Nos | 1 | 1 | 0 | 100%
|  | Shri K. B Tripathi (Mob 9140646160) | PMC Site Engineer | C/o Shri Atma Ram Mishra, Mohoba | [14 empty] | WTP | Nos | 1 | 1 | 0 | 100%
|  |  |  | 1. Neeraj Tripathi (8948727266) | [14 empty] | OHSR | Nos | 18 | 15 | 3 | 83.3%
|  |  |  | 2. Sahil Shams (7014433066) | [7 empty] | Distribution Main Survey | 2020-07-18 | Km | 581.687+ increasing | 581.69 | 100 |  | CWR | Nos | 7 | 6 | 1 | 85.71%
|  |  |  | 3. Md Zaid (8604442856) | [13 empty] | LAND CLEARANCE | INTAKE | Nos | 1 | 1 | 0 | 100%
|  |  |  | 4. Chandan Jain (9760934446) | [14 empty] | WTP | Nos | 1 | 0 | 1 | 0%
|  |  |  | 5. Faraz Hussain (7668475999) | [7 empty] | Soil testing (Boreholes) | 2020-08-13 | Nos | 50 | 21 | 42 |  | OHSR | Nos | 18 | 0 | 18 | 0%
|  |  | SWSM representative | Dinesh Chandra Pandey (Mob-9454866952) | [14 empty] | CWR | Nos | 7 | 0 | 7 | 0%
|  |  | Contractor Nominated | L&T (B.P. Sahu (Mob-9315038398) | [13 empty] | LAND HANDING OVER | INTAKE | Nos | 1 | 0 | 1 | 0%
[12 empty] | Demarcation | 2020-07-05 | Nos | 18 | 17 | 94.4444 |  | WTP | Nos | 1 | 0 | 1 | 0%
[19 empty] | OHSR | Nos | 18 | 0 | 18 | 0%
[19 empty] | CWR | Nos | 7 | 0 | 7 | 0%
2 |  | Salaiya Nathupura G.O.V. W/S Scheme | DPR Agency Nominated Person | BLG (Mr. Khet Singh. Mob 9956221055) | 347.18 | 251.4 | 231.93 | 2020-07-01 | 2020-08-21 | In process | In process | Activities | Start Date | Unit | Planned | Achieved | % Completed | Detail of work | Item | Unit | Scope | Achieved | balance | % Progress | NIL
|  | Arjun Dam | PMC Agency | SMEC India | [7 empty] | Rising main Survey | 2020-07-21 | Km | 239 | 217.4 | 90.9623 | LAND IDENTIFICATION | INTAKE | Nos | 1 | 1 | 0 | 100%
|  | Shri K. B Tripathi (Mob-9140646160) | PMC Site Engineer | C/o Shri Atma Ram Mishra, Mohoba | [14 empty] | WTP | Nos | 1 | 1 | 0 | 100%
|  |  |  | 1. Umesh Pathak (6392028207) | [14 empty] | OHSR | Nos | 41 | 36 | 7 | 87.8%
|  |  |  | 2. Ishwar Tiwari (7748835443) | [7 empty] | Distribution Main Survey | 2020-08-05 | Km | 455 | 437.2 | 96.0879 |  | CWR | Nos | 24 | 19 | 6 | 79.17%
|  |  |  | 3. Ankit Kumar (8130189006) | [13 empty] | LAND CLEARANCE | INTAKE | Nos | 1 | 1 | 0 | 100%
|  |  |  | 4. Krishna Dubey (7982167277) | [14 empty] | WTP | Nos | 1 | 0 | 1 | 0%
|  |  |  | 5. Rishav Saket (7979032227) | [7 empty] | Soil testing ( Boreholes) | 2020-08-07 | Nos | 116 | 52 | 44.8276 |  | OHSR | Nos | 41 | 0 | 41 | 0%
|  |  | SWSM representative | Kashif Mumtaz (Mob-9450782032) | [14 empty] | CWR | Nos | 24 | 0 | 24 | 0%
|  |  | Contractor Nominated | JMC (C.shahnmugam Mob-7974860223) | [13 empty] | LAND HANDING OVER | INTAKE | Nos | 1 | 0 | 1 | 0%
[12 empty] | Demarcation | 2020-07-31 | Nos | 41 | 36 | 87.8049 |  | WTP | Nos | 1 | 1 | 0 | 100%
[19 empty] | OHSR | Nos | 41 | 0 | 41 | 0%
[19 empty] | CWR | Nos | 24 | 0 | 24 | 0%
3- |  | Lahchura kashipura G.O.V. W/S Scheme | DPR Agency Nominated Person | BLG (Mr. Khet Singh. Mob 9956221055) | 316.46 | 204.35 | 208.35 | 2020-07-01 | In Process | In Process | In Process | Activities | Start Date | Unit | Planned | Achieved | % Completed | Detail of work | Item | Unit | Scope | Achieved | balance | % Progress | NIL
|  | Lahchura Dam | PMC Agency | SMEC India | [7 empty] | Rising main Survey | 2020-07-10 | Km | 175 | 148.1 | 84.6286 | LAND IDENTIFICATION | INTAKE | Nos | 1 | 1 | 0 | 100%
|  | Shri K. B Tripathi (Mob-9140646160) | PMC Site Engineer | C/o Shri Atma Ram Mishra, Mohoba | [14 empty] | WTP | Nos | 1 | 1 | 0 | 100%
|  |  |  | 1. Himanshu Singh (7985803882) | [14 empty] | OHSR | Nos | 30 | 21 | 0 | 70%
|  |  |  | 2. Siddharth Singh (7387169069) | [7 empty] | Distribution Main Survey | 2020-09-01 | Km | 372 | 199.1 | 53.5215 |  | CWR | Nos | 10 | 7 | 0 | 70%
|  |  |  | 3. Tejas Bothra (8605033777) | [13 empty] | LAND CLEARANCE | INTAKE | Nos | 1 | 0 | 1 | 0%
|  |  |  | 4. Sanjeeb Jena (7008940363) | [14 empty] | WTP | Nos | 1 | 0 | 1 | 0%
|  |  |  | 5.Rupank Dutta (9981558779) | [7 empty] | Soil testing ( Boreholes) | 2020-08-22 | Nos | 74 | 31 | 41.8919 |  | OHSR | Nos | 30 | 0 | 30 | 0%
|  |  | SWSM representative | Surjeet Singh Gangwar (Mob-9198878286) | [14 empty] | CWR | Nos | 10 | 0 | 10 | 0%
|  |  | Contractor Nominated | JMC (C.shahnmugam Mob-7974860223) | [13 empty] | LAND HANDING OVER | INTAKE | Nos | 1 | 0 | 1 | 0%
[12 empty] | Demarcation | 2020-08-20 | Nos | 31 | 25 | 80.6452 |  | WTP | Nos | 1 | 1 | 0 | 100%
[19 empty] | OHSR | Nos | 30 | 0 | 30 | 0%
[19 empty] | CWR | Nos | 10 | 0 | 10 | 0%
4- |  | kabrai G.O.V. W/S Scheme | DPR Agency Nominated Person | BLG (Mr. Khet Singh. Mob 9956221055) | 225.37 | 134.2 | 131.21 | In Process | In Process | In Process | In Process | ……. | ……. | ……. | ……. | ……. | ……. | ……. | ……. | ……. | ……. | ……. | ……. | ……. | NIL
|  | Kabrai Dam | PMC Agency | SMEC India
|  | Shri K. B Tripathi (Mob-9140646160) | PMC Site Engineer
1. Himanshu Singh (7985803882)
2. Siddharth Singh (7387169069)
3. Tejas Bothra (8605033777)
4. Sanjeeb Jena (7008940363)
5.Rupank Dutta (9981558779)
|  |  | SWSM representative | Surjeet Singh Gangwar (Mob-9198878286)
|  |  | Contractor Nominated | JMC (C.shahnmugam Mob-7974860223)
5 |  | Dhawarra Sijwa G.O.V. W/S Scheme | DPR Agency Nominated Person | BLG (Mr. Khet Singh. Mob 9956221055) | 423.55 | 347.31 | 310.91 | In Process | In Process | In Process | In Process | ……. | ……. | ……. | ……. | ……. | ……. | ……. | ……. | ……. | ……. | ……. | ……. | ……. | NIL
|  | Urmil Dam | PMC Agency | SMEC India
|  | Shri K. B Tripathi (Mob-9140646160) | PMC Site Engineer | C/o Shri Atma Ram Mishra, Mohoba
1. Himanshu Singh (7985803882)
2. Siddharth Singh (7387169069)
3. Tejas Bothra (8605033777)
4. Sanjeeb Jena (7008940363)
5.Rupank Dutta (9981558779)
|  |  | SWSM representative | Surjeet Singh Gangwar (Mob-9198878286)
|  |  | Contractor Nominated | SLC-SMC JV
6 | Banda | Amli kaur G.O.V. W/S Scheme & Tube well scheme(28 Nos) | DPR Agency Nominated Person | REPL Anil Kr Mishra (Mob-7570932555) | 1208.37 | ---- |  | Technical Bid under review | 2020-08-20 | ---- | ---- | ……. | ……. | ……. | ……. | ……. | ……. | ……. | ……. | ……. | ……. | ……. | ……. | ……. | NIL
|  | Yamuna River | PMC Agency | SMEC India
|  | Naveen Verma (9451910381) | PMC Site Engineer | B-136, Awas Vikas Colony, Banda, U.P. 210001, India
|  |  | SWSM representative | Surjeet Singh Gangwar (Mob-9198878286)
Contractor Nominated
7 |  | khatan G.O.V. W/S Scheme | DPR Agency Nominated Person | REPL Krishn Tiwari 7982984837 | 2085.03 | 2109 | 1492.45 | 2020-09-20 | 2020-08-20 |  |  | ……. | ……. | ……. | ……. | ……. | ……. | ……. | ……. | ……. | ……. | ……. | ……. | ……. | NIL
|  | Yamuna River | PMC Agency | SMEC India
|  | Naveen Verma (9451910381) | PMC Site Engineer | 1. Gautam Sashi (7459068017)
2. Shubham Chandra (9580450200)
3. Abhishek Verma (7728911526)
4. Nitin Sharma (9928688036)
5. Ajay Kumar (9818790921)
|  |  | SWSM representative | Surjeet Singh Gangwar (Mob-9198878286)
|  |  | Contractor Nominated | L&T J.V tiwari 8335082210
8- | Chitrakoot | Raipura G.O.V. W/S Scheme | DPR Agency Nominated Person | REPL Abhishek Tiwari 9039864356 | 352.87 | 240.05 | 248.46 | In Process | 2020-09-15 |  |  | ……. | ……. | ……. | ……. | ……. | ……. | ……. | ……. | ……. | ……. | ……. | ……. | ……. | NIL
|  | Gunta Dam | PMC Agency | SMEC India
|  | Naveen Verma (9451910381) | PMC Site Engineer | C/o Shri Sushil Kumar Dwiwedi Rajapur, Chitrakoot, Uttar Pradesh 210207
SWSM representative
|  |  | Contractor Nominated | GVPR Parth upadhyay (9924127653)
9 |  | Bhartaul G.O.V. W/S Scheme | DPR Agency Nominated Person | REPL Abhishek Tiwari 9039864356 | 128.71 | 90.4 | 92.9 | In Process | In Process |  |  | ……. | ……. | ……. | ……. | ……. | ……. | ……. | ……. | ……. | ……. | ……. | ……. | ……. | NIL
|  | Barua Dam | PMC Agency | SMEC India
|  | Naveen Verma (9451910381) | PMC Site Engineer | 1. Jugal Kishore (9748943645)
2. Kuldeep Singh (9548130234)
3. Dinesh Rasila (9915905003)
4. Navjot Singh (9079993916)
5. Shekhar anand rai (8052736798)
SWSM representative
Contractor Nominated
10 |  | Silauta mustkil & Chandi Bangar G.O.V. W/S Scheme | DPR Agency Nominated Person | REPL Anand/Nadeem 7982127142/8127598873 | 1255.69 | --- | 940.57 | 2020-09-21 | 2020-09-15 |  |  | ……. | ……. | ……. | ……. | ……. | ……. | ……. | ……. | ……. | ……. | ……. | ……. | ……. | NIL
|  | Yamuna River | PMC Agency | SMEC India
|  | Naveen Verma (9451910381) | PMC Site Engineer | 1. Jugal Kishore (9748943645)
2. Kuldeep Singh (9548130234)
3. Dinesh Rasila (9915905003)
4. Navjot Singh (9079993916)
5. Shekhar anand rai (8052736798)
SWSM representative
|  |  | Contractor Nominated | L&T J.V tiwari 8335082210