## 
SMEC INTERNATIONAL PVT LTD - Zone 3 Progress Report Dated 28-09-2020
S.No | PMC Alloted Zone /District | Name of Nodal Officer | Scheme Name | Source Name | DPR Agency Nominated Person | PMC Name & Address | PMC Site Engineer & Address | SWSM Representative | Contractor & Nominated Person | NIT No. | NIT Cost |  |  | Contract Award Cost |  |  | BOQ Updating Status 70 LPCD to 55 LPCD | DPR Status 70 LPCD to 55 LPCD |  |  |  | Physical Progress | [5 empty] | Land Details | [6 empty] | Status of Financial Progress
[11 empty] | INR in Crore |  |  | INR in Crore |  |  |  | Date of submission of DPR @55 LPCD | Review by PMC | Date of Vetting By IIT | Date of Approval by competent authority | Activities | Start Date | Unit | Planned | Achieved | % Completed | Detail of work | Item | Unit | Scope | Achieved | Balance | % Progress
[11 empty] | Capex | Opex | Total | Capex | Opex | Total
1 | 2 | 5 | 3 | 4 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
1 | Mahoba | Shri K. B Tripathi (9140646160) | Shivhar G.O.V. W/S Scheme | Chandrawal Dam | BLG Construction Services Ltd. Khet Singh 9956221055 | SMEC India Pvt. Ltd | C/o Shri Atma Ram Mishra Bhatipura, Mahoba, Uttar Pradesh, 210427, India | Dinesh Chandra Pandey (9454866952) | L&T B.p Sahu (9315038398) | 113/W-17/BID/2020-21 Dated: 16.04.2020 | 185.42 | 29.73 | 215.15 | 214.79 | 27.38 | 242.17 | NIL | 2020-09-22 | 2020-09-24 |  |  | Rising main Survey | 2020-07-15 | Km | 158.812+increasing | 158.81 | 100 | LAND IDENTIFICATION | [6 empty] | Mobilisation Amout paid 21.16 cr on 13/07/2020
[29 empty] | INTAKE | Nos | 1 | 1 | 0 | 100%
[29 empty] | WTP | Nos | 1 | 1 | 0 | 100%
[29 empty] | OHSR | Nos | 18 | 15 | 3 | 83.3%
[22 empty] | Distribution Main Survey | 2020-07-18 | Km | 581.687+ increasing | 581.69 | 100 |  | CWR | Nos | 7 | 6 | 1 | 85.71%
[28 empty] | LAND CLEARANCE | INTAKE | Nos | 1 | 1 | 0 | 100%
[7 empty] | 1. Neeraj Tripathi(8948727266) 2. Sahil Shams(7014433066) 3. Md Zaid (8604442856) 4. Chandan Jain(9760934446) 5. Faraz Hussain (7668475999) | [21 empty] | WTP | Nos | 1 | 0 | 1 | 0%
[22 empty] | Soil testing ( Boreholes) | 2020-08-13 | Nos | 50 | 19 | 38 |  | OHSR | Nos | 18 | 0 | 18 | 0%
[29 empty] | CWR | Nos | 7 | 0 | 7 | 0%
[28 empty] | LAND HANDING OVER | INTAKE | Nos | 1 | 0 | 1 | 0%
[22 empty] | Demarcation | 2020-07-05 | Nos | 18 | 17 | 94.4444 |  | WTP | Nos | 1 | 0 | 1 | 0%
[29 empty] | OHSR | Nos | 18 | 0 | 18 | 0%
[29 empty] | CWR | Nos | 7 | 0 | 7 | 0%
2 |  |  | Salaiya Nathupura G.O.V. W/S Scheme | Arjun Dam | BLG Construction Services Ltd. Khet Singh 9956221055 | SMEC India Pvt. Ltd | C/o Shri Atma Ram Mishra Bhatipura, Mahoba, Uttar Pradesh, 210427, India | Kashif Mumtaz (9450782032) | JMC-JWIL JV C.shahnmugam (7974860223) | 115/W-17/BID/2020-21 Dated: 16.04.2020 | 199.3 | 35.08 | 234.38 | 203.79 | 28.14 | 231.93 |  | In process | [16 empty] | NIL
[22 empty] | Rising main Survey | 2020-07-21 | Km | 239 | 217.4 | 90.9623 | LAND IDENTIFICATION | INTAKE | Nos | 1 | 1 | 0 | 100%
[29 empty] | WTP | Nos | 1 | 1 | 0 | 100%
[29 empty] | OHSR | Nos | 41 | 34 | 7 | 82.92%
[22 empty] | Distribution Main Survey | 2020-08-05 | Km | 455 | 409.7 | 90.044 |  | CWR | Nos | 24 | 18 | 6 | 75%
[28 empty] | LAND CLEARANCE | INTAKE | Nos | 1 | 1 | 0 | 100%
[7 empty] | 1. Umesh Pathak(6392028207) 2. Ishwar Tiwari (7748835443) 3. Ankit Kumar (8130189006) 4. Krishna Dubey(7982167277) 5. Rishav Saket(7979032227) | [21 empty] | WTP | Nos | 1 | 0 | 1 | 0%
[22 empty] | Soil testing ( Boreholes) | 2020-08-07 | Nos | 116 | 49 | 42.2414 |  | OHSR | Nos | 41 | 0 | 41 | 0%
[29 empty] | CWR | Nos | 24 | 0 | 24 | 0%
[28 empty] | LAND HANDING OVER | INTAKE | Nos | 1 | 0 | 1 | 0%
[22 empty] | Demarcation | 2020-07-31 | Nos | 41 | 34 | 82.9268 |  | WTP | Nos | 1 | 1 | 0 | 100%
[29 empty] | OHSR | Nos | 41 | 0 | 41 | 0%
[29 empty] | CWR | Nos | 24 | 0 | 24 | 0%
3 |  |  | Lahchura kashipura G.O.V. W/S Scheme | Lahchura Dam | BLG Construction Services Ltd. Bablu Singh 9554984925 | SMEC India Pvt. Ltd | C/o Shri Atma Ram Mishra Bhatipura, Mahoba, Uttar Pradesh, 210427, India | Surjeet Singh Gangwar (9198878286) | JMC-JWIL JV C.shahnmugam (7974860223) | 135/W-17/BID/2020-21 Dated: 16.04.2020 | 183.68 | 28.31 | 211.99 | 185.57 | 22.76 | 208.34 |  | In process | [16 empty] | NIL
[22 empty] | Rising main Survey | 2020-07-10 | Km | 175 | 148.1 | 84.6286 | LAND IDENTIFICATION | INTAKE | Nos | 1 | 1 | 0 | 100%
[29 empty] | WTP | Nos | 1 | 1 | 0 | 100%
[29 empty] | OHSR | Nos | 30 | 21 | 0 | 70%
[22 empty] | Distribution Main Survey | 2020-09-01 | Km | 372 | 122.1 | 32.8226 |  | CWR | Nos | 10 | 7 | 0 | 70%
[28 empty] | LAND CLEARANCE | INTAKE | Nos | 1 | 0 | 1 | 0%
[7 empty] | 1. Himanshu Singh(7985803882) 2. Siddharth Singh(7387169069) 3. Tejas Bothra(8605033777) 4. Sanjeeb Jena (7008940363) 5.Rupank Dutta(9981558779) | [21 empty] | WTP | Nos | 1 | 0 | 1 | 0%
[22 empty] | Soil testing ( Boreholes) | 2020-08-22 | Nos | 74 | 26 | 35.1351 |  | OHSR | Nos | 30 | 0 | 30 | 0%
[29 empty] | CWR | Nos | 10 | 0 | 10 | 0%
[28 empty] | LAND HANDING OVER | INTAKE | Nos | 1 | 0 | 1 | 0%
[22 empty] | Demarcation | 2020-08-20 | Nos | 31 | 19 | 61.2903 |  | WTP | Nos | 1 | 1 | 0 | 100%
[29 empty] | OHSR | Nos | 30 | 0 | 30 | 0%
[29 empty] | CWR | Nos | 10 | 0 | 10 | 0%
4 |  |  | kabrai G.O.V. W/S Scheme | Kabrai Dam | BLG Construction Services Ltd. Bablu Singh 9554984925 | SMEC India Pvt. Ltd |  |  |  | 114/W-17/BID/2020-21 Dated: 16.04.2020 | 119 | 17 | 136 | 114.62 | 16.59 | 131.21 |  | Not Updated |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | NIL
5 |  |  | Dhawarra Sijwa G.O.V. W/S Scheme | Urmil Dam | BLG Construction Services Ltd. Bablu Singh 9554984925 | SMEC India Pvt. Ltd |  |  | SLC-SMC JV | 136/W-17/BID/2020-21 Dated: 17.04.2020 | 268.98 | 41.95 | 310.93 | 276.89 | 34.02 | 310.91 |  | Not Updated |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | NIL
6 | Banda | Naveen Verma (9451910381) | Amli kaur G.O.V. W/S Scheme & Tube well scheme(28 Nos) | Yamuna River | REPL Anil Kr Mishra 7570932555 | SMEC India Pvt. Ltd | Sri Rasraj Mishra, S/0 Atmaram Mishra, Indra Nagar, Phase-2, In Front of HL Inter College, Banda, Uttar Pradesh-210001 |  |  | 190/W-17/BID/2020-21 Dated: 07.05.2020 | 690 | 103 | 793 |  |  |  |  | Not Updated |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | NIL
7 |  |  | khatan G.O.V. W/S Scheme | Yamuna River | REPL Krishn Tiwari 7982984837 | SMEC India Pvt. Ltd | 1. Gautam Sashi(7459068017) 2. Shubham Chandra(9580450200) 3. Abhishek Verma (7728911526) 4. Nitin Sharma (9928688036) 5. Ajay Kumar(9818790921) |  | L&T J.V tiwari 8335082210 | 229/W-17/BID/2020-21 Dated: 09.05.2020 | 1290 | 190 | 1480 | 1340.18 | 152.27 | 1492.45 |  | Not Updated |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | NIL
8 | Chitrakoot |  | Raipura G.O.V. W/S Scheme | Gunta Dam | REPL Abhishek Tiwari 9039864356 | SMEC India Pvt. Ltd | C/o Shri Sushil Kumar Dwiwedi Rajapur, Chitrakoot, Uttar Pradesh 210207 |  | GVPR Parth upadhyay (9924127653) | 112/W-17/BID/2020-21 Dated: 16.04.2020 | 211.32 | 35.84 | 247.16 | 220.08 | 28.38 | 248.46 |  | Not Updated |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | NIL
9 |  |  | Bhartaul G.O.V. W/S Scheme | Barua Dam | REPL Abhishek Tiwari 9039864356 | SMEC India Pvt. Ltd | 1. Jugal Kishore(9748943645) 2. Kuldeep Singh(9548130234) 3. Dinesh Rasila(9915905003) 4. Navjot Singh(9079993916) 5. Shekhar Anand Rai(8052736798) |  |  | 139/W-17/BID/2020-21 Dated: 18.04.2020 | 83 | 13 | 96 | 80.2 | 12.7 | 92.9 |  | Not Updated |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | NIL
10 |  |  | Silauta mustkil & Chandi Bangar G.O.V. W/S Scheme | Yamuna River | REPL Anand/Nadeem 7982127142/8127598873 | SMEC India Pvt. Ltd |  |  | L&T J.V tiwari 8335082210 | 189/W-17/BID/2020-21 Dated: 07.05.2020 | 810 | 120 | 930 | 840.37 | 100.2 | 940.57 |  | Not Updated |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | NIL